## Sample Budget
123 Main Street
PROJECT DETAILS |  | SOFT COSTS |  |  | Cost | Amount Due
Finished Sq. Ft. | 3052 | Acquisition Costs |  |  | 0 | 0
# of Bedrooms | 3 | Construction Loan Fees |  |  | 230 | 230
# of Full Bathrooms | 2 | Property Taxes |  |  | 0 | 0
# of Half Bathrooms | 1 | Sales Agent Fee |  |  | 8510 | 8510
Rehab Cost Per Square Foot | 99.2182
Estimated Sales Price | 185000 | Subtotal |  |  | 8740 | 8740
Description | Subcontractor | Estimated Cost | Actual Cost | Variance | Current Paid | Amount Due
GENERAL REQUIREMENTS
Architectural Plans and Specifications |  | 7000 | 7000 |  | 7000
Permits: Building, Foundations, Grading, Retaining Walls | City of Cincinnati | 1500 | 1130 | 370 | 1130
Survey
Civil Engineering
Structural Engineering
Asbestos Survey |  | 600 | 600 |  | 600
Asbestos Abatement |  | 2300 | 1960 | 340 | 1960
Other Misc. Fees
Subtotal |  | 11400 | 10690 | 710 | 10690 | 0
SITE PREP
Building Demolition
Wall Demolition
Erosion Control
Dumpsters |  | 500 | 500 |  | 250 | 250
Dirt Work
Retaining Walls |  | 18500 | 18500 |  | 15000 | 3500
Asphalt/Concrete |  | 15000 | 15000 |  |  | 15000
Waterproofing
Misc.
Subtotal |  | 34000 | 34000 | 0 | 15250 | 18750
UTILITIES
Storm Sewer | contractor & MSD
Sanitary Sewer | contractor & MSD
Sanitary Tap Allowance |  | 600 |  | 600
Water Line | contractor / GCWW | 1500 | 1200 | 300 |  | 1200
Water Tap Allowance |  | 600 |  | 600
Gas Line | contractor / Duke
Electric | Duke | 0
Subtotal |  | 1500 | 1200 | 300 |  | 1200
Including Allowances |  | 2700 | 1200 | 1500 | 0 | 1200
CONSTRUCTION
Demo |  | 45000 | 45000 |  | 45000
Foundations and Footers |  | 1200 | 3400 | -2200 | 3400
Framing |  | 14755 | 14755 |  | 14755
Roofing |  | 9800 | 9800 |  | 9800
Exterior trim and decks |  | 5230 | 5230 |  |  | 5230
Siding /Gutters |  | 19054 | 19054 |  | 19054
Doors and Trim |  | 7350 | 7350 |  | 3200 | 4150
Plumbing |  | 20000 | 20000 |  | 14000 | 6000
HVAC |  | 14000 | 14000 |  | 12000 | 2000
Electrical & Lighting |  | 12000 | 12000 |  | 7400 | 4600
Insulation |  | 5433 | 5433 |  | 5433
Drywall |  | 16430 | 16430 |  | 9000 | 7430
Millwork and Trim |  | 5424 | 5424 |  | 1400 | 4024
Cabinets |  | 9555 | 9555 |  | 4700 | 4855
Countertops |  | 6250 | 6250 |  |  | 6250
Carpet |  | 3600 | 3600 |  |  | 3600
Tile |  | 4076 | 4076 |  | 2000 | 2076
Windows/Glass Block |  | 14600 | 14600 |  | 14600
Landscaping/Tree Removal |  | 5200 | 5200 |  |  | 5200
Bathroom accessories and shelving
Appliances |  | 3050 | 3050 |  |  | 3050
Final Clean |  | 300 | 300 |  |  | 300
Backyard Fence |  | 1500 | 1500 |  |  | 1500
Supervision |  | 22177 | 22177 |  | 12700 | 9477
Subtotal |  | 245984 | 248184 | -2200 | 178442 | 69742
TOTAL CONSTRUCTION COSTS |  | 302824 | 302814 | 10 | 213122 | 98432
SAMPLE
SAMPLE

## Contractor List
Organization | Service Type | Vendor Contact | Vendor Phone | Vendor Email | Vendor Address
A1 Quality Home Improvement & Roofing | Residential Task | lisa Stewart | 513-967-1604 | pvtdata@aol.com | 4727 Loretta Ave.
Abel Building Systems | Install Security Alarm | Dave Menker | 513-772-0401 | dmabel@fuse.net | 47 Techview Drive
Allgeier and Son Inc. | Start Demolition | Michael E. Allgeier | 513-218-7670 | mike@allgeierandson.com | 6386 Bridgetown Road
Alliance and Sons | Conduct Rehab Property Assessment, Residential Task, Secure Property, Renovate Property, Clean Out Property, Remove Litter | Robert Stone | 513-578-8864 | rstone8309@gmail.com | 6424 Glenmont
Allison Landscaping Inc | Cut Grass - Routine, Cut Grass - Nuisance Condition | Bob Lake | 513-922-1313 | Bob@allisonlandscaping.com | 889 Anderson Ferry Rd.
Apartment Ready | Remove Litter - Nuisance, Electrical, Roof Repair, Plumbing Repair, Residential Task, Secure Property, General Property Maintenance, Conduct Initial Property Inspection, Plumbing, Remove Litter - Routine, Clean Out Property, Dump Cleanup, Remove Litter | Warner Johnson | 513-314-4086 | apartmentready513@gmail.com | 1418 Shenandoah Ave
Avon Home Improvements, Inc. | Conduct Rehab Property Assessment, Residential Task, Conduct Initial Property Inspection, Renovate Property | JD Sandipher | 513-961-5323 | jdahirenovate@fuse.net | PO box 19563
B&H Elite complete lawn and garden care | Cut Grass - Routine, Residential Task, Remove Snow, Secure Property, General Property Maintenance, Remove Trees, Cut Grass - Nuisance Condition, Remove Litter - Routine, Clean Out Property, Remove Litter | Steven Scales | 513-314-3817 | bh_elite1@yahoo.com | 5138 Colerain Ave.
Battle Axe Construction LLC | Start Demolition | Joseph Jackson | 513-874-4695 | jackjoe.battleaxeconstruction@gmail.com | 8050 Beckett Center Drive Suite 203
Building Value LLC | Start Demolition | David Rich | 513-475-6783 | drich@buildingvalue.org | 4040 Spring Grove Avenue
Camp Washington (Joe Gorman) | Cut Grass - Routine, Secure Property, Remove Litter - Routine
CDK Construction | Residential Task | Chris Knipper | 513-207-4787 | cdkconstruction@yahoo.com | 207 Olive Branch Rd.
Chase Construction | Clean Out Property, Conduct Rehab Property Assessment, Cut Grass - Nuisance Condition, Cut Grass - Routine, Install Security Fence, Remove Litter, Remove Litter - Routine, Remove Snow, Remove Trees, Renovate Property, Residential Task, Secure Property | Alan Shaw | 513-382-7588 | Alan@thechaseguys.com | 8631 Stillwater Isle
Currybuilt Remodeling | Secure Property, General Property Maintenance, Remove Trees, Renovate Property, Clean Out Property, Dump Cleanup | Nicholas Curry | 513-623-8540 | Currybuilt79@icloud.com | 5376 Scarlet oak Dr.
Dwight Cooke | Remove Trees | Dwight Cooke | 513-430-6181 |  | 3709 Charloe Court
Environmental Demolition Group ,LLC | Abate Asbestos | Shawn McGinness | 859-363-4863 | smcginness@edgllc.biz | 3520 Turfway Road,
Epic Towing | Remove Abandoned Vehicles | NickWhitmire | 513-692-0777 | A1autosource.nw@gmail.com | 800 South cooper
Fiscus Trucking and Excavating, Inc. | Start Demolition | Natalie Fiscus | 513-505-2738 | natalie@fiscusinc.com | 4782 Eastedrn Avenue
Freeman Services LLC. | General Property Maintenance, Clean Out Property | Ryan Freeman | 513-633-0607 | Freemandemolition@gmail.com | 7400 Bernard Ave
HGC Construction Company | Renovate Property | Craig Preston | 513-861-8866 | cpreston@hgcconstruction.com | 2814 Stanton Avenue
Hyde Park Electrical construction LLC | Secure Property, General Property Maintenance, Remove Litter - Routine, Clean Out Property, Remove Litter | John Bowers | 513-815-0933 | hydeparkelectrician@gmail.com | 2413 Findlater
Just Right Construction and Lawn Care | Clean Out Property, Cut Grass - Nuisance Condition, Cut Grass - Routine, Dump Cleanup, General Property Maintenance, Remove Litter, Remove Litter - Nuisance, Remove Litter - Routine, Residential Task, Secure Property | Jamon Lee | 513-379-5052 | justrightconstruction@aol.com | 1172 W. Galbraith Rd. Suite 209
Keep Cincinnati Beautiful | General Property Maintenance, Cut Grass - Nuisance Condition, Remove Litter - Routine, Remove Litter | Katie Davis | 513-352-4381 | katie@keepcincinnatibeautiful.org | 1115 Bates Avenue
Kerkan Roofing Inc. | Commercial Task | Jim Dieringer | 513-821-0556 | jimd@kerkan.com | 721 W. Wyoming Ave.
Kings Lawn Care and Snow Removal | Cut Grass - Routine, Cut Grass - Nuisance Condition | Jermaine King | 513-349-2510 | kingslwncare@yahoo.com | PO Box 18938
Lawn Life | Clean Out Property, Commercial Task, Conduct Initial Property Inspection, Cut Grass - Nuisance Condition, Cut Grass - Routine, Dump Cleanup, General Property Maintenance, Install Security Fence, Remove Litter, Remove Litter - Nuisance, Remove Litter - Routine, Remove Snow, Residential Task, Roof Repair, Secure Property | Tim Arnold | 513-961-2222 | support@lawnlife.org | 3002 Woodburn Avenue
Logan Creek LLC | Start Demolition | Wendell Hansel | 513-200-0057 | whansel@fuse.net | 11360 US Highway 50
Love Landscaping | Cut Grass - Nuisance Condition, Cut Grass - Routine, Remove Snow | Mike Walters | 513-772-4050 | Mike@LoveLandscaping.com | 65 Terrace Dr.
MAC Paran Consulting Group | Conduct Phase I Environmental Survey, Conduct Phase II Environmental Survey, Perform Asbestos Survey | Michelle Paraniuk | 513-752-9111 | macparan@macparan.com | 3953 Fulton Grove Rd.
Maximum Fire Protection | Commercial Task | Renee Hoderlein | 859-640-5415 | renee@max-fp.com | 50 West Techne Center Dr. St. G
Miracle Renovations | Renovate Property | Merrick Collins | 513-371-0750 | collinsmerrick@yahoo.com | 2786 Shaffer Ave.
Moore Air | HVAC | Amanda Kimbrell | 513-772-3444 | Amanda.Kimbrell@bmes-hvac.com | 175 Tri-County Pkwy #50
Onyx Termite & Pest Control | Abate Pests/Termites | Leonard Phipps | 513-721-2847 | onyxtermite@gmail.com | 5734 Gilmore Drive
O'Rourke Wrecking Company | Abate Asbestos, Start Demolition | Jeff Sizemore | 513-871-1400 | jsizemore@orourkewrecking.com | 660 Lunken Park Drive
Pandey Environmental, LLC | Conduct Phase I Environmental Survey | Atul Pandey | (614) 444-8078 x207 | info@pandeyenvironmental.com | 4100 Horizons Drive Suite 205
Partner Engineering and Science, Inc. | Conduct Rehab Property Assessment, Prepare Architectual Drawings, Conduct Phase I Environmental Survey, Conduct Phase II Environmental Survey | Robert Knight | 513-315-7931 | bknight@partneresi.com | 312 Walnut St. Suite 1130
Pinnacle Environmental Consultants, Inc. | Conduct Phase I Environmental Survey, Perform Asbestos Survey | Mike Strine | 513.533.1823 | MStrine@pinnacleinc.biz | 486 Old State Route 74
Platte Architecture + Design | Prepare Architectual Drawings | Melissa Reddy | 513-871-1850 | melissa@plattedesign.com | 202 West Elder, 4th Floor
Rainbow Environmental Services, Inc. | Abate Asbestos, Create Asbestos Abatement Bid Spec, Perform Asbestos Survey | Jon French | 513-624-6470 | Resifrench@aol.com | P.O. Box 54863
Rave Landscaping | Cut Grass - Nuisance Condition, Cut Grass - Routine, Remove Litter - Nuisance, Remove Litter - Routine | Mark Rave | 513-439-4372 | Mark.Rave.Mr@gmail.com | 5207 Highview Dr.
Ron Taylor Repair Co. | Clean Out Property, Conduct Initial Property Inspection, Cut Grass - Nuisance Condition, Cut Grass - Routine, Dump Cleanup, General Property Maintenance, Install Security Fence, Remove Graffiti, Remove Litter, Remove Litter - Nuisance, Remove Litter - Routine, Remove Snow, Residential Task, Roof Repair, Secure Property | Ron Taylor | 513-921-7096 | artaylor1942@gmail.com | 980 Kirbert Ave.
Seco Electric Company inc. | Electrical | Joe Schamer | 859-491-2984 | joes@secoelectric.net | 350 Pike St.
Site Solutions Consulting LLC | Create Demolition Report | Tim Myers | 513-532-2269 | tmyers@sitesolutionsconsulting.com | 1050 Sagebrush Court
Structural Systems Repair, LLC | Stabilize Property | Walter Weed | 513-751-7774 | wweed@ssrg.com | 2824 Stanton Avenue
Sustainergy Cooperative | Residential Task | Flequer Vera | 513-244-2700 | sustainergy@sustainergy.coop> | 4211 Williamson Pl.
The Spring Clean Co. LLC | Remove Litter - Nuisance, General Property Maintenance, Remove Litter - Routine, Clean Out Property, Dump Cleanup, Remove Litter | H. Coleman Henderson | 513-3442267 | coleman201475@gmail.com | 2530 stanton Ave.
Triton Services HVAC | Residential Task | Majid Samarghandi | 513-679-6800 |  | 8162 Duke Blvd.
Ultra Technic Construction | Secure Property, General Property Maintenance, Renovate Property, Stabilize Property | Olusegun Akomolede | 513-615-2966 | akomolede@aol.com | 6531 West Chester Rd.
Voegele Services LLC | Start Demolition | Steve Voegele | 812-212-2747 | 1voegelellc@gmail.com | 21166 Beacon Rd.
Xcell Building Maintenance | Remove Litter - Nuisance, Electrical, Roof Repair, Plumbing Repair, Residential Task, Secure Property, General Property Maintenance, Conduct Initial Property Inspection, Plumbing, Remove Litter - Routine, Clean Out Property, Dump Cleanup, Remove Litter | Lamaure White | 513-461-4077 | xcellbuildingmaint@gmail.com | 6206 Meyers Dr.

## Blank Budget Template
123 Main Street
PROJECT DETAILS |  | SOFT COSTS |  |  | Cost | Amount Due
Finished Sq. Ft. |  | Acquisition Costs |  |  | 0 | 0
# of Bedrooms |  | Construction Loan Fees |  |  | 0 | 0
# of Full Bathrooms |  | Property Taxes |  |  | 0 | 0
# of Half Bathrooms |  | Sales Agent Fee |  |  | 0 | 0
Rehab Cost Per Square Foot | #DIV/0!
Estimated Sales Price |  | Subtotal |  |  | 0 | 0
Description | Subcontractor | Estimated Cost | Actual Cost | Variance | Current Paid | Amount Due
GENERAL REQUIREMENTS
Architectural Plans and Specifications
Permits: Building, Foundations, Grading, Retaining Walls
Survey
Civil Engineering
Structural Engineering
Asbestos Survey
Asbestos Abatement
Other Misc. Fees
Subtotal |  | 0 | 0 | 0 | 0 | 0
SITE PREP
Building Demolition
Wall Demolition
Erosion Control
Dumpsters
Dirt Work
Retaining Walls
Asphalt/Concrete
Waterproofing
Misc.
Subtotal |  | 0 | 0 | 0 | 0
UTILITIES
Storm Sewer
Sanitary Sewer
Sanitary Tap Allowance
Water Line
Water Tap Allowance
Gas Line
Electric
Subtotal |  | 0 | 0
Including Allowances |  | 0 | 0 |  | 0
CONSTRUCTION
Demo
Foundations and Footers
Framing
Roofing
Exterior trim and decks
Siding /Gutters
Doors and Trim
Plumbing
HVAC
Electrical & Lighting
Insulation
Drywall
Millwork and Trim
Cabinets
Countertops
Carpet
Tile
Windows/Glass Block
Landscaping/Tree Removal
Bathroom accessories and shelving
Appliances
Final Clean
Backyard Fence
Supervision
Subtotal |  | 0 | 0 |  | 0 | 0
TOTAL CONSTRUCTION COSTS |  | 0 | 0 |  | 0 | #VALUE!